## Sheet1
Order Number | Work Order Description | WO St | WO St | W.O. Type | WO Type | Priority | Priority | Serial Number | Equipment Description | Status Comment | Reference | Order Date | Planned Start Date | Planned Finish Date | Requested Finish Date | Actual Finish Date | Flash Message | Flash Message Description | % Cmp | Estimated Hours | Actual Hours | Business Unit | Business Unit Description | Customer Number | Customer Name | Originator Number | Originator Description | Crew | Manager/Planner Description | Supervisor | Supervisor Description | Assigned To | Assigned To Description | Parent W.O. | Inventory Number | Plant Code | Phase Description | Plant Area | Cat 02 Description | Sub Area | Cat 03 Description | Work Type | Cat 04 Description | Cond. Code | Cat 05 Description | Sta | Sta Description | Call Out | Srv Typ Description | Equipment Class | Skl Typ Description | Criticality Code | Exp Lvl Description | WO Cat | WO Cat Description | Or Ty | Or Ty Description | Estimated Downtime | Case Number | Lease Number | Branch | Branch Description | Unit | Site Number | Contact Name | Contract Number | Contract Type | Contract Type Description | Serial Number | Unit Number | Lead Craft | Lead Craft Description
221901 | SPARE MOTOR ,CHECK AS ROTOR F/ | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 3 | WIthin a Week - Default | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) |  | CL-HP4420 | 2003-03-12 | 2003-03-12 | 22/12/03 | 2003-03-12 | 15/12/03 |  | . |  | 48 | 33 | 11764140 | Unit 1 | 1175 | PT CABOT INDONESIA | 22536 | ADIKORA UTARAWANTO | [6 empty] | 00221901 | CL-GA00015 | CL | Cilegon | 01 | UNIT 01 | 0C | REACTORS | 21 | PREVENTIVE |  | NO SHUT DOWN REQUIRED |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS |  |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT CABOT INDONESIA
230540 | *PM* DIAL KE-EKSENTRISAN PULLE | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 3 | WIthin a Week - Default | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) |  | CL-HP4420 | 22/12/03 | 22/12/03 | 22/12/03 | 22/12/03 | 2004-03-03 |  | . |  | 4 |  | 11764140 | Unit 1 | 1175 | PT CABOT INDONESIA | 22425 | A. BUDAIRY YUSI | [6 empty] | 00211083 | CL-GA00015 | CL | Cilegon | 01 | UNIT 01 | 0C | REACTORS | 21 | PREVENTIVE | S3 | UNIT / LINE SHUT DOWN |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS |  |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT CABOT INDONESIA
254408 | MONTHLY VIB CHECK | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 3 | WIthin a Week - Default | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) |  | CL-HP4420 | 16/02/04 | 16/02/04 | 16/02/04 | 16/02/04 | 2004-03-03 |  | . |  |  |  | 11764140 | Unit 1 | 1175 | PT CABOT INDONESIA | 22538 | DWI YULIANTO | 22538 | DWI YULIANTO | 22541 | HASAN BASRI |  |  | 00254408 | CL-GA00015 | CL | Cilegon | 01 | UNIT 01 | 0C | REACTORS | 22 | PREDICTIVE |  | NO SHUT DOWN REQUIRED |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS |  |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT CABOT INDONESIA
270099 | UKUR VIBRASI MESIN | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 3 | WIthin a Week - Default | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) |  | CL-HP4420 | 19/03/04 | 19/03/04 | 19/03/04 | 19/03/04 | 2004-08-04 |  | . |  |  |  | 11764140 | Unit 1 | 1175 | PT CABOT INDONESIA | 22538 | DWI YULIANTO | 22541 | HASAN BASRI |  |  |  |  | 00270099 | CL-GA00015 | CL | Cilegon | 01 | UNIT 01 | 0C | REACTORS | 12 | CORRECTIVE | S4 | OFF-LOAD / OFF-LINE |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS |  |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT CABOT INDONESIA
316584 | CHECK ROTOJET PUMP 15 KARENA | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 3 | WIthin a Week - Default | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) |  | CL-HP4420 | 29/06/04 | 29/06/04 | 29/06/04 | 29/06/04 | 16/07/04 |  | . |  | 2 | 65 | 11764140 | Unit 1 | 1175 | PT CABOT INDONESIA | 22421 | SYARIP HIDAYAT | 22541 | HASAN BASRI |  |  |  |  | 00316584 | CL-GA00015 | CL | Cilegon | 01 | UNIT 01 | 0C | REACTORS | 12 | CORRECTIVE |  | NO SHUT DOWN REQUIRED |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS |  |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT CABOT INDONESIA
335921 | BEARING UNTUK SPARE POMPA | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 3 | WIthin a Week - Default | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) | Done | CL-HP4420 | 2004-10-08 | 2004-10-08 | 2004-10-08 | 2004-10-08 | 2005-04-10 |  | . |  |  | 166 | 11764140 | Unit 1 | 1175 | PT CABOT INDONESIA | 22545 | TRIMARYANTO TRIMARYANTO |  |  | 22545 | TRIMARYANTO TRIMARYANTO |  |  | 00335921 | CL-GA00015 | CL | Cilegon | 01 | UNIT 01 | 0C | REACTORS | 21 | PREVENTIVE |  | NO SHUT DOWN REQUIRED |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS |  |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT CABOT INDONESIA
392568 | ASSEMBLY ROTOR UNTUK SPARE | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 3 | WIthin a Week - Default | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) |  | CL-HP4420 | 2004-09-12 | 2004-09-12 | 2004-09-12 | 2004-09-12 | 20/12/04 |  | . |  |  | 8 | 11764420 | Raw Material Handling | 1175 | PT CABOT INDONESIA | 22545 | TRIMARYANTO TRIMARYANTO |  |  | 22545 | TRIMARYANTO TRIMARYANTO |  |  | 00392568 | CL-GA00015 | CL | Cilegon | 20 | OPERATING MAINTENANCE | 7K | RAW MATERIAL HANDLING | 21 | PREVENTIVE |  | NO SHUT DOWN REQUIRED |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS |  |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT CABOT INDONESIA
397313 | CHECK VIBRASI | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 3 | WIthin a Week - Default | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) |  | CL-HP4420 | 20/12/04 | 20/12/04 | 20/12/04 | 20/12/04 | 20/12/04 |  | . |  |  | 24 | 11764420 | Raw Material Handling | 1175 | PT CABOT INDONESIA | 22538 | DWI YULIANTO |  |  | 22538 | DWI YULIANTO |  |  | 00397313 | CL-GA00015 | CL | Cilegon | 20 | OPERATING MAINTENANCE | 7K | RAW MATERIAL HANDLING |  | DEFAULT |  | NO SHUT DOWN REQUIRED |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS |  |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT CABOT INDONESIA
415964 | GANTI BELT ROTOJET GA 00-00-15 | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 3 | WIthin a Week - Default | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) |  | CL-HP4420 | 31/01/05 | 31/01/05 | 31/01/05 | 31/01/05 | 2005-11-02 |  | . |  |  | 8 | 11764420 | Raw Material Handling | 1175 | PT CABOT INDONESIA | 22423 | YUNIANTO WIBOWO |  |  | 22545 | TRIMARYANTO TRIMARYANTO |  |  | 00415964 | CL-GA00015 | CL | Cilegon | 20 | OPERATING MAINTENANCE | 7K | RAW MATERIAL HANDLING | 21 | PREVENTIVE |  | NO SHUT DOWN REQUIRED |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS |  |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT CABOT INDONESIA
426937 | BELI PULLEY POMPA& MOTOR | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 3 | WIthin a Week - Default | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) |  | CL-HP4420 | 23/02/05 | 23/02/05 | 23/02/05 | 23/02/05 | 28/04/05 |  | . |  | 4 |  | 11764420 | Raw Material Handling | 1175 | PT CABOT INDONESIA | 22545 | TRIMARYANTO TRIMARYANTO |  |  | 22545 | TRIMARYANTO TRIMARYANTO |  |  | 00426937 | CL-GA00015 | CL | Cilegon | 20 | OPERATING MAINTENANCE | 7K | RAW MATERIAL HANDLING | 21 | PREVENTIVE |  | NO SHUT DOWN REQUIRED |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS |  |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT CABOT INDONESIA
436544 | BEARING MOTOR NOISE DAN PPOMPA | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 3 | WIthin a Week - Default | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) |  | CL-HP4420 | 15/03/05 | 15/03/05 | 15/03/05 | 15/03/05 | 20/05/05 |  | . |  |  | 23 | 11764420 | Raw Material Handling | 1175 | PT CABOT INDONESIA | 22545 | TRIMARYANTO TRIMARYANTO |  |  | 22545 | TRIMARYANTO TRIMARYANTO |  |  | 00436544 | CL-GA00015 | CL | Cilegon | 20 | OPERATING MAINTENANCE | 7K | RAW MATERIAL HANDLING | 21 | PREVENTIVE |  | NO SHUT DOWN REQUIRED |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS |  |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT CABOT INDONESIA
447368 | CHECK ROTO JET | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 3 | WIthin a Week - Default | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) | Done | CL-HP4420 | 2005-06-04 | 2005-06-04 | 2005-06-04 | 2005-06-04 | 19/09/05 |  | . |  |  | 30 | 11764420 | Raw Material Handling | 1175 | PT CABOT INDONESIA | 22423 | YUNIANTO WIBOWO |  |  | 22545 | TRIMARYANTO TRIMARYANTO |  |  | 00447368 | CL-GA00015 | CL | Cilegon | 20 | OPERATING MAINTENANCE | 7K | RAW MATERIAL HANDLING | 11 | REACTIVE |  | NO SHUT DOWN REQUIRED |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS |  |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT CABOT INDONESIA
455250 | GANTI BEARING MOTOR | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 3 | WIthin a Week - Default | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) | ganti motor baru | CL-HP4420 | 21/04/05 | 21/04/05 | 21/04/05 | 21/04/05 | 17/05/05 |  | . |  |  | 127 | 11764420 | Raw Material Handling | 1175 | PT CABOT INDONESIA | 22423 | YUNIANTO WIBOWO |  |  | 22545 | TRIMARYANTO TRIMARYANTO |  |  | 00455250 | CL-GA00015 | CL | Cilegon | 20 | OPERATING MAINTENANCE | 7K | RAW MATERIAL HANDLING | 11 | REACTIVE |  | NO SHUT DOWN REQUIRED |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS |  |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT CABOT INDONESIA
470454 | GANTI BELT YANG PUTUS ROTO JET | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 3 | WIthin a Week - Default | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) |  | CL-HP4420 | 22/05/05 | 22/05/05 | 22/05/05 | 22/05/05 | 23/05/05 |  | . |  |  | 16 | 11764420 | Raw Material Handling | 1175 | PT CABOT INDONESIA | 22414 | M. YUNUS BACHRUN |  |  | 22545 | TRIMARYANTO TRIMARYANTO |  |  | 00470454 | CL-GA00015 | CL | Cilegon | 20 | OPERATING MAINTENANCE | 7K | RAW MATERIAL HANDLING | 21 | PREVENTIVE |  | NO SHUT DOWN REQUIRED |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS |  |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT CABOT INDONESIA
504762 | LAPPING MECH SEAL | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 3 | WIthin a Week - Default | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) |  | CL-HP4420 | 2005-02-08 | 2005-02-08 | 2005-02-08 | 2005-02-08 | 2005-05-10 |  | . |  |  |  | 11764420 | Raw Material Handling | 1175 | PT CABOT INDONESIA | 22545 | TRIMARYANTO TRIMARYANTO |  |  | 22545 | TRIMARYANTO TRIMARYANTO |  |  | 00504762 | CL-GA00015 | CL | Cilegon | 20 | OPERATING MAINTENANCE | 7K | RAW MATERIAL HANDLING | 21 | PREVENTIVE |  | NO SHUT DOWN REQUIRED |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS |  |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT CABOT INDONESIA
534565 | ROTOJET GA-15 CHECK VIBRASI | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 3 | WIthin a Week - Default | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) | ganti pompa | CL-HP4420 | 2005-04-10 | 2005-04-10 | 2005-04-10 | 2005-04-10 | 2005-10-10 |  | . |  |  | 8 | 11764420 | Raw Material Handling | 1175 | PT CABOT INDONESIA | 22418 | SRI HANANTO |  |  | 22545 | TRIMARYANTO TRIMARYANTO |  |  | 00534565 | CL-GA00015 | CL | Cilegon | 20 | OPERATING MAINTENANCE | 7K | RAW MATERIAL HANDLING | 22 | PREDICTIVE |  | NO SHUT DOWN REQUIRED |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS |  |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT CABOT INDONESIA
627347 | GANTI MECHANIC SEAL | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 3 | WIthin a Week - Default | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) | ganti seal krn bocor | CL-HP4420 | 14/04/06 | 14/04/06 | 14/04/06 | 14/04/06 | 25/04/06 |  | . |  |  | 11 | 11764420 | Raw Material Handling | 1175 | PT CABOT INDONESIA | 22423 | YUNIANTO WIBOWO |  |  | 22545 | TRIMARYANTO TRIMARYANTO |  |  | 00627347 | CL-GA00015 | CL | Cilegon | 20 | OPERATING MAINTENANCE | 7K | RAW MATERIAL HANDLING | 12 | CORRECTIVE |  | NO SHUT DOWN REQUIRED |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS |  |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT CABOT INDONESIA
665682 | GANTI ROTOR ROTOJET PUMP 15 | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 3 | WIthin a Week - Default | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) | Diganti 1 set | CL-HP4420 | 2006-03-07 | 2006-03-07 | 2006-03-07 | 2006-03-07 | 2006-06-07 |  | . |  |  | 103 | 11764420 | Raw Material Handling | 1175 | PT CABOT INDONESIA | 22419 | SUPRIYANTO SUPRIYANTO |  |  | 22545 | TRIMARYANTO TRIMARYANTO |  |  | 00665682 | CL-GA00015 | CL | Cilegon | 20 | OPERATING MAINTENANCE | 7K | RAW MATERIAL HANDLING | 22 | PREDICTIVE |  | NO SHUT DOWN REQUIRED |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS |  |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT CABOT INDONESIA
713198 | ASSEMBLY POMPA FOR SPARE | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 3 | WIthin a Week - Default | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) |  | CL-HP4420 | 2006-06-10 | 2006-06-10 | 2006-06-10 | 2006-06-10 | 18/10/06 |  | . |  |  | 40 | 11764420 | Raw Material Handling | 1175 | PT CABOT INDONESIA | 22545 | TRIMARYANTO TRIMARYANTO |  |  | 22545 | TRIMARYANTO TRIMARYANTO |  |  | 00713198 | CL-GA00015 | CL | Cilegon | 20 | OPERATING MAINTENANCE | 7K | RAW MATERIAL HANDLING | 21 | PREVENTIVE |  | NO SHUT DOWN REQUIRED |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS |  |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT CABOT INDONESIA
755798 | CHECK / BELT & PULLEY GANTI JI | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 3 | WIthin a Week - Default | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) | reseting tension | CL-HP4420 | 21/12/06 | 21/12/06 | 21/12/06 | 21/12/06 | 23/01/07 |  | . |  |  |  | 11764420 | Raw Material Handling | 1175 | PT CABOT INDONESIA | 22545 | TRIMARYANTO TRIMARYANTO |  |  | 22545 | TRIMARYANTO TRIMARYANTO |  |  | 00755798 | CL-GA00015 | CL | Cilegon | 20 | OPERATING MAINTENANCE | 7K | RAW MATERIAL HANDLING | 21 | PREVENTIVE |  | NO SHUT DOWN REQUIRED |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS |  |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT CABOT INDONESIA
979328 | CHANGE MECANICAL SEAL POMPA RO | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 3 | WIthin a Week - Default | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) |  | CL-HP4420 | 2008-10-01 | 2008-10-01 | 2008-10-01 | 2008-10-01 | 21/01/08 |  | . |  |  |  | 11764420 | Raw Material Handling | 1175 | PT CABOT INDONESIA | 22423 | YUNIANTO WIBOWO |  |  | 22545 | TRIMARYANTO TRIMARYANTO |  |  | 00979328 | CL-GA00015 | CL | Cilegon | 20 | OPERATING MAINTENANCE | 7K | RAW MATERIAL HANDLING | 21 | PREVENTIVE |  | NO SHUT DOWN REQUIRED |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS |  |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT CABOT INDONESIA
994146 | CUSTOM CLEARANCE ROTOJET PUMP | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 3 | WIthin a Week - Default | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) |  | CL-HP4420 | 2008-04-02 | 2008-04-02 | 2008-04-02 | 2008-04-02 | 2008-09-07 |  | . |  |  |  | 11764420 | Raw Material Handling | 1175 | PT CABOT INDONESIA | 168384 | YUSUF GUNAWAN | [6 empty] | 00994146 | CL-GA00015 | CL | Cilegon | 20 | OPERATING MAINTENANCE | 7K | RAW MATERIAL HANDLING | 21 | PREVENTIVE |  | NO SHUT DOWN REQUIRED |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS |  |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT CABOT INDONESIA
1017879 | GANTI BELT KARENA PUTUS | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 3 | WIthin a Week - Default | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) | ganti belt as XPB 2410x6 | CL-HP4420 | 14/03/08 | 14/03/08 | 14/03/08 | 14/03/08 | 18/03/08 |  | . |  |  | 8 | 11764420 | Raw Material Handling | 1175 | PT CABOT INDONESIA | 22423 | YUNIANTO WIBOWO |  |  | 22545 | TRIMARYANTO TRIMARYANTO |  |  | 01017879 | CL-GA00015 | CL | Cilegon | 20 | OPERATING MAINTENANCE | 7K | RAW MATERIAL HANDLING | 11 | REACTIVE |  | NO SHUT DOWN REQUIRED |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS |  |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT CABOT INDONESIA
1031167 | BELI PULLEY | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 3 | WIthin a Week - Default | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) |  | CL-HP4420 | 2008-07-04 | 2008-07-04 | 2008-07-04 | 2008-07-04 | 23/05/08 |  | . |  |  |  | 11764420 | Raw Material Handling | 1175 | PT CABOT INDONESIA | 22545 | TRIMARYANTO TRIMARYANTO | [6 empty] | 01031167 | CL-GA00015 | CL | Cilegon | 20 | OPERATING MAINTENANCE | 7K | RAW MATERIAL HANDLING |  | DEFAULT |  | NO SHUT DOWN REQUIRED |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS |  |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT CABOT INDONESIA
1047526 | GANTI V-BELT ROTOJET PUMP CL-2 | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 3 | WIthin a Week - Default | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) | ganti belt karena mulai rusak | CL-HP4420 | 2008-06-05 | 2008-06-05 | 2008-06-05 | 2008-06-05 | 2008-12-05 |  | . |  |  | 31 | 11764420 | Raw Material Handling | 1175 | PT CABOT INDONESIA | 22415 | MULYADI HARIS ABDULLAH | [6 empty] | 01047526 | CL-GA00015 | CL | Cilegon | 20 | OPERATING MAINTENANCE | 7K | RAW MATERIAL HANDLING |  | DEFAULT |  | NO SHUT DOWN REQUIRED |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS |  |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT CABOT INDONESIA
1090965 | GANTI MOTOR | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 3 | WIthin a Week - Default | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) | done | CL-HP4420 | 22/07/08 | 22/07/08 | 22/07/08 | 22/07/08 | 2008-12-08 |  | . |  |  | 107 | 11764420 | Raw Material Handling | 1175 | PT CABOT INDONESIA | 22423 | YUNIANTO WIBOWO |  |  | 22536 | ADIKORA UTARAWANTO |  |  | 01090965 | CL-GA00015 | CL | Cilegon | 20 | OPERATING MAINTENANCE | 7K | RAW MATERIAL HANDLING | 11 | REACTIVE |  | NO SHUT DOWN REQUIRED |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS |  |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT CABOT INDONESIA
1263237 | TOLONG DI GANTI PRESS GAUGE PO | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 3 | WIthin a Week - Default | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) | done | CL-HP4420 | 19/07/09 | 21/07/09 | 21/07/09 | 21/07/09 | 2009-08-09 |  | . |  |  |  | 11764420 | Raw Material Handling | 1175 | PT CABOT INDONESIA | 22405 | DADANG ZULKIFLI |  |  | 22543 | PARDIONO PARDIONO |  |  | 01263237 | CL-GA00015 | CL | Cilegon | 20 | OPERATING MAINTENANCE | 7K | RAW MATERIAL HANDLING | 12 | CORRECTIVE |  | NO SHUT DOWN REQUIRED |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS |  |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT CABOT INDONESIA
1311464 | GANTI BELT POMPA ROTO JET | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 3 | WIthin a Week - Default | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) | ganti belt ok | CL-HP4420 | 27/10/09 | 27/10/09 | 27/10/09 | 27/10/09 | 2009-03-11 |  | . |  |  |  | 11764420 | Raw Material Handling | 1175 | PT CABOT INDONESIA | 22545 | TRIMARYANTO TRIMARYANTO | [6 empty] | 01311464 | CL-GA00015 | CL | Cilegon | 20 | OPERATING MAINTENANCE | 7K | RAW MATERIAL HANDLING |  | DEFAULT |  | NO SHUT DOWN REQUIRED |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS |  |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT CABOT INDONESIA
1329226 | CHECK PUMP ROTOJET U2 GA-00015 | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 3 | WIthin a Week - Default | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) | ganti belt ok | CL-HP4420 | 2009-02-12 | 2009-02-12 | 2009-02-12 | 2009-02-12 | 2009-10-12 |  | . |  |  | 4 | 11764420 | Raw Material Handling | 1175 | PT CABOT INDONESIA | 22418 | SRI HANANTO |  |  | 22545 | TRIMARYANTO TRIMARYANTO |  |  | 01329226 | CL-GA00015 | CL | Cilegon | 20 | OPERATING MAINTENANCE | 7K | RAW MATERIAL HANDLING | 12 | CORRECTIVE |  | NO SHUT DOWN REQUIRED |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS |  |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT CABOT INDONESIA
1481489 | BELT KENDOR | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 3 | WIthin a Week - Default | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) | ganti belt saat SD ok | CL-HP4420 | 23/09/10 | 23/08/10 | 23/09/10 | 23/09/10 | 2010-12-10 |  | . |  |  |  | 11764420 | Raw Material Handling | 1175 | PT CABOT INDONESIA | 22545 | TRIMARYANTO TRIMARYANTO |  |  | 22545 | TRIMARYANTO TRIMARYANTO |  |  | 01481489 | CL-GA00015 | CL | Cilegon | 20 | OPERATING MAINTENANCE | 7K | RAW MATERIAL HANDLING | 32 | COMPLIANCE MAINTENANCE |  | NO SHUT DOWN REQUIRED |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS |  |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT CABOT INDONESIA
3208182 | ROTOJET PUMP U2 | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 3 | WIthin a Week - Default | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) | done | CL-HP4420 | 2011-06-11 | 2011-06-11 | 2011-06-11 |  | 2011-11-11 |  | . | 100 | 4 | 3 | 11764420 | Raw Material Handling | 1175 | PT CABOT INDONESIA | 22545 | TRIMARYANTO TRIMARYANTO |  |  | 22545 | TRIMARYANTO TRIMARYANTO |  |  | 03208182 | CL-GA00015 | CL | Cilegon | 20 | OPERATING MAINTENANCE | 7K | RAW MATERIAL HANDLING | 32 | COMPLIANCE MAINTENANCE |  | NO SHUT DOWN REQUIRED |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS | 4 |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT. CABOT INDONESIA |  |  |  | CL-GA00015
3244957 | ROTOJET PUMP GA-00015,EM | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 1 | Today (Now) | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) | DONE | CL-HP4420 | 28/01/12 | 28/01/12 | 28/01/12 |  | 2012-08-02 |  | . | 100 | 4 |  | 11764420 | Raw Material Handling | 1175 | PT CABOT INDONESIA | 22418 | SRI HANANTO |  |  | 22545 | TRIMARYANTO TRIMARYANTO |  |  | 03244957 | CL-GA00015 | CL | Cilegon | 20 | OPERATING MAINTENANCE | 7K | RAW MATERIAL HANDLING | 11 | REACTIVE |  | NO SHUT DOWN REQUIRED |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS | 4 |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT. CABOT INDONESIA |  |  |  | CL-GA00015
3310056 | REPAIR ROTO JET PUMP U2 | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 3 | WIthin a Week - Default | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) | ganti unit pompa OK | CL-HP4420 | 16/06/12 | 16/06/12 | 22/06/12 |  | 21/06/12 |  | . | 100 | 4 | 73.5 | 11764420 | Raw Material Handling | 1175 | PT CABOT INDONESIA | 22423 | YUNIANTO WIBOWO |  |  | 22545 | TRIMARYANTO TRIMARYANTO |  |  | 03310056 | CL-GA00015 | CL | Cilegon | 20 | OPERATING MAINTENANCE | 7K | RAW MATERIAL HANDLING | 32 | COMPLIANCE MAINTENANCE |  | NO SHUT DOWN REQUIRED |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS | 4 |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT. CABOT INDONESIA |  |  |  | CL-GA00015
3429581 | CHECK POMPA ROTOJET GA-00015 | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 3 | WIthin a Week - Default | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) | done | CL-HP4420 | 13/03/13 | 29/03/13 | 29/03/13 |  | 24/09/13 |  | . | 100 | 4 |  | 11764420 | Raw Material Handling | 1175 | PT CABOT INDONESIA | 22423 | YUNIANTO WIBOWO |  |  | 22545 | TRIMARYANTO TRIMARYANTO |  |  | 03429581 | CL-GA00015 | CL | Cilegon | 20 | OPERATING MAINTENANCE | 7K | RAW MATERIAL HANDLING | 32 | COMPLIANCE MAINTENANCE |  | NO SHUT DOWN REQUIRED |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS | 4 |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT. CABOT INDONESIA |  |  |  | CL-GA00015
3507488 | CONTACTOR | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 3 | WIthin a Week - Default | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) | done | CL-HP4420 | 2013-02-09 | 2013-02-09 | 19/09/13 |  | 15/01/14 |  | . | 100 | 4 |  | 11764420 | Raw Material Handling | 1175 | PT CABOT INDONESIA | 22405 | DADANG ZULKIFLI |  |  | 22537 | DODIK T. HANDOKO |  |  | 03507488 | CL-GA00015 | CL | Cilegon | 20 | OPERATING MAINTENANCE | 7K | RAW MATERIAL HANDLING | 21 | PREVENTIVE |  | NO SHUT DOWN REQUIRED |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS | 4 |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT. CABOT INDONESIA |  |  |  | CL-GA00015
3526118 | ROTOJET PUMP 02 NOISE | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 1 | Today (Now) | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) | complete | CL-HP4420 | 2013-07-10 | 2013-07-10 | 2013-11-10 |  | 2013-09-10 |  | . | 100 | 4 | 86.5 | 11764420 | Raw Material Handling | 1175 | PT CABOT INDONESIA | 22405 | DADANG ZULKIFLI |  |  | 22545 | TRIMARYANTO TRIMARYANTO |  |  | 03526118 | CL-GA00015 | CL | Cilegon | 20 | OPERATING MAINTENANCE | 7K | RAW MATERIAL HANDLING | 11 | REACTIVE |  | NO SHUT DOWN REQUIRED |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS | 4 |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT. CABOT INDONESIA |  |  |  | CL-GA00015
3526176 | tolong check pompa 15 ngorok | 98 | CANCELLED | R | Maintenance Request | 3 | WIthin a Week - Default | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) |  | CL-HP4420 | 2013-07-10 | 2013-07-10 | 2013-07-10 |  | 2013-07-10 |  | . | 100 | 4 |  | 11764420 | Raw Material Handling | 1175 | PT CABOT INDONESIA | 22545 | TRIMARYANTO TRIMARYANTO |  |  | 22545 | TRIMARYANTO TRIMARYANTO |  |  | 03526176 | CL-GA00015 | CL | Cilegon | 20 | OPERATING MAINTENANCE | 7K | RAW MATERIAL HANDLING |  | DEFAULT |  | NO SHUT DOWN REQUIRED |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS | 4 |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT. CABOT INDONESIA |  |  |  | CL-GA00015
3557256 | CONTACTOR ROTOJETPUMP | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 3 | WIthin a Week - Default | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) | DONE | CL-HP4420 | 22/11/13 | 22/11/13 | 26/11/13 |  | 25/11/13 |  | . | 100 | 4 |  | 11764420 | Raw Material Handling | 1175 | PT CABOT INDONESIA | 22405 | DADANG ZULKIFLI |  |  | 22537 | DODIK T. HANDOKO |  |  | 03557256 | CL-GA00015 | CL | Cilegon | 20 | OPERATING MAINTENANCE | 7K | RAW MATERIAL HANDLING | 21 | PREVENTIVE | S3 | UNIT / LINE SHUT DOWN |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS | 4 |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT. CABOT INDONESIA |  |  |  | CL-GA00015
3627049 | ROTOJET FS U2 FIBRASI | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 2 | Tomorrow (within 24 hours) | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) | done | CL-HP4420 | 22/03/14 | 22/03/14 | 2014-02-04 |  | 2014-02-04 |  | . | 100 | 4 | 69 | 11764420 | Raw Material Handling | 1175 | PT CABOT INDONESIA | 22418 | SRI HANANTO |  |  | 22545 | TRIMARYANTO TRIMARYANTO |  |  | 03627049 | CL-GA00015 | CL | Cilegon | 20 | OPERATING MAINTENANCE | 7K | RAW MATERIAL HANDLING | 12 | CORRECTIVE |  | NO SHUT DOWN REQUIRED |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS | 4 |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT. CABOT INDONESIA |  |  |  | CL-GA00015
3661549 | VALVE DISCH POMPA U2 REMBES | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 3 | WIthin a Week - Default | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) | ganti valve ok | CL-HP4420 | 21/05/14 | 21/05/14 | 21/05/14 |  | 14/04/15 |  | . | 100 | 4 |  | 11764420 | Raw Material Handling | 1175 | PT CABOT INDONESIA | 22405 | DADANG ZULKIFLI |  |  | 22545 | TRIMARYANTO TRIMARYANTO |  |  | 03661549 | CL-GA00015 | CL | Cilegon | 20 | OPERATING MAINTENANCE | 7K | RAW MATERIAL HANDLING | 21 | PREVENTIVE | S3 | UNIT / LINE SHUT DOWN |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS | 4 |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT. CABOT INDONESIA |  |  |  | CL-GA00015
3689282 | ampere tinggi | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 3 | WIthin a Week - Default | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) | DONE | CL-HP4420 | 2014-08-07 | 2014-08-07 | 2014-08-07 |  | 2014-10-07 |  | . | 100 | 4 |  | 11764420 | Raw Material Handling | 1175 | PT CABOT INDONESIA | 22545 | TRIMARYANTO TRIMARYANTO | [6 empty] | 03689282 | CL-GA00015 | CL | Cilegon | 20 | OPERATING MAINTENANCE | 7K | RAW MATERIAL HANDLING | 21 | PREVENTIVE |  | NO SHUT DOWN REQUIRED |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS | 4 |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT CABOT INDONESIA |  |  |  | CL-GA00015
3803566 | SEAL BEARING ROTOJET U2 BOCOR | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 3 | WIthin a Week - Default | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) | done | CL-HP4420 | 30/01/15 | 30/01/15 | 30/01/15 |  | 2015-12-03 |  | . | 100 | 4 |  | 11764420 | Raw Material Handling | 1175 | PT CABOT INDONESIA | 22418 | SRI HANANTO |  |  | 22545 | TRIMARYANTO TRIMARYANTO |  |  | 03803566 | CL-GA00015 | CL | Cilegon | 20 | OPERATING MAINTENANCE | 7K | RAW MATERIAL HANDLING | 21 | PREVENTIVE |  | NO SHUT DOWN REQUIRED |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS | 4 |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT CABOT INDONESIA |  |  |  | CL-GA00015
3874788 | rotor jet pump 15 | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 3 | WIthin a Week - Default | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) | done | CL-HP4420 | 29/05/15 | 29/05/15 | 29/05/15 |  | 2015-04-06 |  | . | 100 | 4 |  | 11764420 | Raw Material Handling | 1175 | PT CABOT INDONESIA | 22545 | TRIMARYANTO TRIMARYANTO |  |  | 22545 | TRIMARYANTO TRIMARYANTO |  |  | 03874788 | CL-GA00015 | CL | Cilegon | 20 | OPERATING MAINTENANCE | 7K | RAW MATERIAL HANDLING | 21 | PREVENTIVE |  | NO SHUT DOWN REQUIRED |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS | 4 |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT CABOT INDONESIA |  |  |  | CL-GA00015
3922996 | MOTOR ROTOJET PUMP TRIP | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 3 | WIthin a Week - Default | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) | done | CL-HP4420 | 23/08/15 | 23/08/15 | 23/08/15 |  | 25/08/15 |  | . | 100 | 4 | 18 | 11764420 | Raw Material Handling | 1175 | PT CABOT INDONESIA | 22405 | DADANG ZULKIFLI |  |  | 22537 | DODIK T. HANDOKO |  |  | 03922996 | CL-GA00015 | CL | Cilegon | 20 | OPERATING MAINTENANCE | 7K | RAW MATERIAL HANDLING | 21 | PREVENTIVE |  | NO SHUT DOWN REQUIRED |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS | 4 |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT CABOT INDONESIA |  |  |  | CL-GA00015
3936242 | ROTOJET PUMP U2 BOCOR | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 3 | WIthin a Week - Default | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) | done | CL-HP4420 | 15/09/15 | 15/09/15 | 15/09/15 |  | 23/10/15 |  | . | 100 | 4 | 48 | 11764420 | Raw Material Handling | 1175 | PT CABOT INDONESIA | 22405 | DADANG ZULKIFLI |  |  | 22545 | TRIMARYANTO TRIMARYANTO |  |  | 03936242 | CL-GA00015 | CL | Cilegon | 20 | OPERATING MAINTENANCE | 7K | RAW MATERIAL HANDLING | 21 | PREVENTIVE |  | NO SHUT DOWN REQUIRED |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS | 4 |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT CABOT INDONESIA |  |  |  | CL-GA00015
3966848 | V BELT ROTOJET PUMP U2 NGEBUL | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 3 | WIthin a Week - Default | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) | done | CL-HP4420 | 2015-06-11 | 2015-06-11 | 2015-06-11 |  | 19/11/15 |  | . | 100 | 4 |  | 11764420 | Raw Material Handling | 1175 | PT CABOT INDONESIA | 22405 | DADANG ZULKIFLI |  |  | 22545 | TRIMARYANTO TRIMARYANTO |  |  | 03966848 | CL-GA00015 | CL | Cilegon | 20 | OPERATING MAINTENANCE | 7K | RAW MATERIAL HANDLING | 21 | PREVENTIVE |  | NO SHUT DOWN REQUIRED |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS | 4 |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT CABOT INDONESIA |  |  |  | CL-GA00015
4018651 | FLOW POMPA LOW | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 3 | WIthin a Week - Default | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) |  | CL-HP4420 | 2016-09-02 | 2016-09-02 | 2016-09-02 |  | 2016-12-02 |  | . | 100 | 4 |  | 11764420 | Raw Material Handling | 1175 | PT CABOT INDONESIA | 22405 | DADANG ZULKIFLI |  |  | 807400 | HENDRO CAHYONO |  |  | 04018651 | CL-GA00015 | CL | Cilegon | 20 | OPERATING MAINTENANCE | 7K | RAW MATERIAL HANDLING | 21 | PREVENTIVE |  | NO SHUT DOWN REQUIRED |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS | 4 |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT CABOT INDONESIA |  |  |  | CL-GA00015
4018652 | PRESS GAUGE ROTOJET | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 3 | WIthin a Week - Default | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) |  | CL-HP4420 | 2016-09-02 | 2016-09-02 | 2016-09-02 |  | 20/06/16 |  | . | 100 | 4 | 10 | 11764420 | Raw Material Handling | 1175 | PT CABOT INDONESIA | 22405 | DADANG ZULKIFLI |  |  | 22537 | DODIK T. HANDOKO |  |  | 04018652 | CL-GA00015 | CL | Cilegon | 20 | OPERATING MAINTENANCE | 7K | RAW MATERIAL HANDLING | 21 | PREVENTIVE |  | NO SHUT DOWN REQUIRED |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS | 4 |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT CABOT INDONESIA |  |  |  | CL-GA00015
4041725 | POMPA VIBRASI | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 3 | WIthin a Week - Default | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) |  | CL-HP4420 | 20/03/16 | 20/03/16 | 20/03/16 |  | 31/03/16 |  | . | 100 | 4 | 14.5 | 11764420 | Raw Material Handling | 1175 | PT CABOT INDONESIA | 22405 | DADANG ZULKIFLI |  |  | 807400 | HENDRO CAHYONO |  |  | 04041725 | CL-GA00015 | CL | Cilegon | 20 | OPERATING MAINTENANCE | 7K | RAW MATERIAL HANDLING | 21 | PREVENTIVE |  | NO SHUT DOWN REQUIRED |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS | 4 |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT CABOT INDONESIA |  |  |  | CL-GA00015
4070005 | Ganti Kipas Rotojet motor CL 2 | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 3 | WIthin a Week - Default | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) |  | CL-HP4420 | 2016-09-05 | 2016-09-05 | 2016-09-05 |  | 2016-02-06 |  | . | 100 | 4 | 13 | 11764420 | Raw Material Handling | 1175 | PT CABOT INDONESIA | 22415 | MULYADI HARIS ABDULLAH |  |  | 22537 | DODIK T. HANDOKO |  |  | 04070005 | CL-GA00015 | CL | Cilegon | 20 | OPERATING MAINTENANCE | 7K | RAW MATERIAL HANDLING |  | DEFAULT |  | NO SHUT DOWN REQUIRED |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS | 4 |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT CABOT INDONESIA |  |  |  | CL-GA00015
4094849 | SHAFT PUMP BROKEN | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 3 | WIthin a Week - Default | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) | Done | CL-HP4420 | 18/06/16 | 18/06/16 | 18/06/16 |  | 23/06/16 |  | . | 100 | 4 |  | 11764420 | Raw Material Handling | 1175 | PT CABOT INDONESIA | 22405 | DADANG ZULKIFLI |  |  | 807400 | HENDRO CAHYONO |  |  | 04094849 | CL-GA00015 | CL | Cilegon | 20 | OPERATING MAINTENANCE | 7K | RAW MATERIAL HANDLING | 21 | PREVENTIVE |  | NO SHUT DOWN REQUIRED |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS | 4 |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT CABOT INDONESIA |  |  |  | CL-GA00015
4153298 | Install ampere Rotojet 3 | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 3 | WIthin a Week - Default | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) |  | CL-HP4420 | 28/09/16 | 28/09/16 | 28/09/16 |  | 2016-04-10 |  | . | 100 | 4 | 13.5 | 11764420 | Raw Material Handling | 1175 | PT CABOT INDONESIA | 22415 | MULYADI HARIS ABDULLAH |  |  | 22537 | DODIK T. HANDOKO |  |  | 04153298 | CL-GA00015 | CL | Cilegon | 20 | OPERATING MAINTENANCE | 7K | RAW MATERIAL HANDLING |  | DEFAULT |  | NO SHUT DOWN REQUIRED |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS | 4 |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT CABOT INDONESIA |  |  |  | CL-GA00015
4260912 | BELT MULAI KENDOR | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 3 | WIthin a Week - Default | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) |  | CL-HP4420 | 27/03/17 | 27/03/17 | 27/03/17 |  | 29/03/17 |  | . | 100 | 4 |  | 11764420 | Raw Material Handling | 1175 | PT CABOT INDONESIA | 365570 | HABIBULLAH HABIBULLAH |  |  | 807400 | HENDRO CAHYONO |  |  | 04260912 | CL-GA00015 | CL | Cilegon | 20 | OPERATING MAINTENANCE | 7K | RAW MATERIAL HANDLING | 21 | PREVENTIVE |  | NO SHUT DOWN REQUIRED |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS | 4 |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT CABOT INDONESIA |  |  |  | CL-GA00015
4311680 | Repair Rotojet fs pump U2 | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 3 | WIthin a Week - Default | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) |  | CL-HP4420 | 20/06/17 | 20/06/17 | 20/06/17 |  | 2017-10-07 |  | . | 100 | 4 |  | 11764420 | Raw Material Handling | 1175 | PT CABOT INDONESIA | 56781 | AFIFI AFIFI | 339442 | LUKAS HERMAWAN | 807400 | HENDRO CAHYONO |  |  | 04311680 | CL-GA00015 | CL | Cilegon | 20 | OPERATING MAINTENANCE | 7K | RAW MATERIAL HANDLING | 21 | PREVENTIVE |  | NO SHUT DOWN REQUIRED |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS | 4 |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT CABOT INDONESIA |  |  |  | CL-GA00015
4322910 | ROTOJET GA0015 | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 3 | WIthin a Week - Default | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) |  | CL-HP4420 | 2017-10-07 | 2017-10-07 | 2017-10-07 |  | 2017-11-07 |  | . | 100 | 4 | 8 | 11764420 | Raw Material Handling | 1175 | PT CABOT INDONESIA | 22419 | SUPRIYANTO SUPRIYANTO |  |  | 807400 | HENDRO CAHYONO |  |  | 04322910 | CL-GA00015 | CL | Cilegon | 20 | OPERATING MAINTENANCE | 7K | RAW MATERIAL HANDLING | 22 | PREDICTIVE |  | NO SHUT DOWN REQUIRED |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS | 4 |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT CABOT INDONESIA |  |  |  | CL-GA00015
4464305 | ROTOJET GA-15 BELT PUTUS 1BH | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 3 | WIthin a Week - Default | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) |  | CL-HP4420 | 24/11/17 | 24/11/17 | 24/11/17 |  | 27/11/17 |  | . | 100 | 4 | 4 | 11764420 | Raw Material Handling | 1175 | PT CABOT INDONESIA | 22419 | SUPRIYANTO SUPRIYANTO |  |  | 807400 | HENDRO CAHYONO |  |  | 04464305 | CL-GA00015 | CL | Cilegon | 20 | OPERATING MAINTENANCE | 7K | RAW MATERIAL HANDLING |  | DEFAULT |  | NO SHUT DOWN REQUIRED |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS | 4 |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT CABOT INDONESIA |  |  |  | CL-GA00015
4489463 | Repair guarding Rotojet GA15 | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 3 | WIthin a Week - Default | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) |  | CL-HP4420 | 2018-09-01 | 2018-09-01 | 2018-09-01 |  | 13/03/18 |  | . | 100 | 4 |  | 11764420 | Raw Material Handling | 1175 | PT CABOT INDONESIA | 56781 | AFIFI AFIFI | 339442 | LUKAS HERMAWAN | 807400 | HENDRO CAHYONO |  |  | 04489463 | CL-GA00015 | CL | Cilegon | 20 | OPERATING MAINTENANCE | 7K | RAW MATERIAL HANDLING | 21 | PREVENTIVE |  | NO SHUT DOWN REQUIRED |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS | 4 |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT CABOT INDONESIA |  |  |  | CL-GA00015
4578443 | Repair Rotojet pump 15 | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 3 | WIthin a Week - Default | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) | Done | CL-HP4420 | 2018-05-06 | 2018-05-06 | 2018-05-06 |  | 20/08/22 |  | . |  | 4 | 20 | 11764420 | Raw Material Handling | 1175 | PT CABOT INDONESIA | 56781 | AFIFI AFIFI | 339442 | LUKAS HERMAWAN | 807400 | HENDRO CAHYONO |  |  | 04611716 | CL-GA00015 | CL | Cilegon | 20 | OPERATING MAINTENANCE | 7K | RAW MATERIAL HANDLING | 21 | PREVENTIVE |  | NO SHUT DOWN REQUIRED |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS | 4 |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT CABOT INDONESIA |  |  |  | CL-GA00015
4657519 | Repair grating selokan pump h | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 3 | WIthin a Week - Default | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) |  | CL-HP4420 | 18/10/18 | 18/10/18 | 18/10/18 |  | 21/10/18 |  | . | 100 | 4 |  | 11764420 | Raw Material Handling | 1175 | PT CABOT INDONESIA | 56781 | AFIFI AFIFI | 339442 | LUKAS HERMAWAN | 807400 | HENDRO CAHYONO |  |  | 04657519 | CL-GA00015 | CL | Cilegon | 20 | OPERATING MAINTENANCE | 7K | RAW MATERIAL HANDLING | 21 | PREVENTIVE |  | NO SHUT DOWN REQUIRED |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS | 4 |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT CABOT INDONESIA |  |  |  | CL-GA00015
4727879 | Ganti pompa rotojet U2 | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 3 | WIthin a Week - Default | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) |  | CL-HP4420 | 18/02/19 | 18/02/19 | 18/02/19 |  | 19/02/19 |  | . | 100 | 4 | 8 | 11764420 | Raw Material Handling | 1175 | PT CABOT INDONESIA | 56781 | AFIFI AFIFI | 339442 | LUKAS HERMAWAN | 807400 | HENDRO CAHYONO |  |  | 04472747 | CL-GA00015 | CL | Cilegon | 20 | OPERATING MAINTENANCE | 7K | RAW MATERIAL HANDLING | 21 | PREVENTIVE | S3 | UNIT / LINE SHUT DOWN |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS | 4 |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT CABOT INDONESIA |  |  |  | CL-GA00015
4727884 | Ganti motor rotojet U-2 | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 3 | WIthin a Week - Default | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) |  | CL-HP4420 | 18/02/19 | 18/02/19 | 18/02/19 |  | 19/02/19 |  | . | 100 | 4 |  | 11764420 | Raw Material Handling | 1175 | PT CABOT INDONESIA | 56781 | AFIFI AFIFI | 339442 | LUKAS HERMAWAN | 22537 | DODIK T. HANDOKO |  |  | 04727884 | CL-GA00015 | CL | Cilegon | 20 | OPERATING MAINTENANCE | 7K | RAW MATERIAL HANDLING | 21 | PREVENTIVE |  | NO SHUT DOWN REQUIRED |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS | 4 |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT CABOT INDONESIA |  |  |  | CL-GA00015
4730534 | Ganti V-Belt | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 3 | WIthin a Week - Default | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) |  | CL-HP4420 | 22/02/19 | 22/02/19 | 22/02/19 |  | 22/02/19 |  | . | 100 | 4 |  | 11764420 | Raw Material Handling | 1175 | PT CABOT INDONESIA | 22415 | MULYADI HARIS ABDULLAH |  |  | 807400 | HENDRO CAHYONO |  |  | 04730534 | CL-GA00015 | CL | Cilegon | 20 | OPERATING MAINTENANCE | 7K | RAW MATERIAL HANDLING | 32 | COMPLIANCE MAINTENANCE |  | NO SHUT DOWN REQUIRED |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS | 4 |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT CABOT INDONESIA |  |  |  | CL-GA00015
4767640 | Ganti bearing Rotojet GA 15 | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 3 | WIthin a Week - Default | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) |  | CL-HP4420 | 26/04/19 | 26/04/19 | 26/04/19 |  | 26/04/19 |  | . | 100 | 4 |  | 11764420 | Raw Material Handling | 1175 | PT CABOT INDONESIA | 22415 | MULYADI HARIS ABDULLAH |  |  | 807400 | HENDRO CAHYONO |  |  | 04767640 | CL-GA00015 | CL | Cilegon | 20 | OPERATING MAINTENANCE | 7K | RAW MATERIAL HANDLING | 32 | COMPLIANCE MAINTENANCE |  | NO SHUT DOWN REQUIRED |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS | 4 |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT CABOT INDONESIA |  |  |  | CL-GA00015
4821267 | Repair rotojet fsk pump | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 3 | WIthin a Week - Default | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) | Done | CL-HP4420 | 31/07/19 | 31/07/19 | 31/07/19 |  | 2019-01-08 |  | . | 100 | 4 |  | 11764420 | Raw Material Handling | 1175 | PT CABOT INDONESIA | 56781 | AFIFI AFIFI | 339442 | LUKAS HERMAWAN | 807400 | HENDRO CAHYONO |  |  | 04821267 | CL-GA00015 | CL | Cilegon | 20 | OPERATING MAINTENANCE | 7K | RAW MATERIAL HANDLING | 21 | PREVENTIVE |  | NO SHUT DOWN REQUIRED |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS | 4 |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT CABOT INDONESIA |  |  |  | CL-GA00015
4833913 | Pasang PG di outlet Pump FS 15 | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 3 | WIthin a Week - Default | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) |  | CL-HP4420 | 23/08/19 | 23/08/19 | 23/08/19 |  | 23/08/19 |  | . | 100 | 4 |  | 11764420 | Raw Material Handling | 1175 | PT CABOT INDONESIA | 22415 | MULYADI HARIS ABDULLAH |  |  | 22537 | DODIK T. HANDOKO |  |  | 04833913 | CL-GA00015 | CL | Cilegon | 20 | OPERATING MAINTENANCE | 7K | RAW MATERIAL HANDLING |  | DEFAULT |  | NO SHUT DOWN REQUIRED |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS | 4 |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT CABOT INDONESIA |  |  |  | CL-GA00015
4842475 | Cek suction v/v rotojet pump15 | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 3 | WIthin a Week - Default | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) |  | CL-HP4420 | 2019-06-09 | 2019-06-09 | 2019-06-09 |  | 18/09/19 |  | . | 100 | 4 |  | 11764420 | Raw Material Handling | 1175 | PT CABOT INDONESIA | 56781 | AFIFI AFIFI | 339442 | LUKAS HERMAWAN | 807400 | HENDRO CAHYONO |  |  | 04842475 | CL-GA00015 | CL | Cilegon | 20 | OPERATING MAINTENANCE | 7K | RAW MATERIAL HANDLING | 21 | PREVENTIVE |  | NO SHUT DOWN REQUIRED |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS | 4 |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT CABOT INDONESIA |  |  |  | CL-GA00015
4877726 | Ganti 1 set rotojet pump 15 | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 3 | WIthin a Week - Default | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) |  | CL-HP4420 | 2019-08-11 | 2019-08-11 | 2019-08-11 |  | 2019-11-11 |  | . | 100 | 4 |  | 11764420 | Raw Material Handling | 1175 | PT CABOT INDONESIA | 56781 | AFIFI AFIFI | 998307 | RICKY SUWIGNJO | 807400 | HENDRO CAHYONO |  |  | 04877726 | CL-GA00015 | CL | Cilegon | 20 | OPERATING MAINTENANCE | 7K | RAW MATERIAL HANDLING | 21 | PREVENTIVE |  | NO SHUT DOWN REQUIRED |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS | 4 |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT CABOT INDONESIA |  |  |  | CL-GA00015
4922618 | Ganti beraing rotojet | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 3 | WIthin a Week - Default | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) |  | CL-HP4420 | 31/01/20 | 31/01/20 | 31/01/20 |  | 31/01/20 |  | . | 100 | 4 | 24 | 11764420 | Raw Material Handling | 1175 | PT CABOT INDONESIA | 22415 | MULYADI HARIS ABDULLAH |  |  | 807400 | HENDRO CAHYONO |  |  | 04922618 | CL-GA00015 | CL | Cilegon | 20 | OPERATING MAINTENANCE | 7K | RAW MATERIAL HANDLING | 45 | OTHER |  | NO SHUT DOWN REQUIRED |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS | 4 |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT CABOT INDONESIA |  |  |  | CL-GA00015
4923350 | POMPA ROTOJET CL1 & CL2 BELT M | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 3 | WIthin a Week - Default | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) |  | CL-HP4420 | 2020-02-02 | 2020-02-02 | 2020-02-02 |  | 2020-07-02 |  | . | 100 | 4 |  | 11764420 | Raw Material Handling | 1175 | PT CABOT INDONESIA | 365570 | HABIBULLAH HABIBULLAH |  |  | 807400 | HENDRO CAHYONO |  |  | 04923350 | CL-GA00015 | CL | Cilegon | 20 | OPERATING MAINTENANCE | 7K | RAW MATERIAL HANDLING | 21 | PREVENTIVE |  | NO SHUT DOWN REQUIRED |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS | 4 |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT CABOT INDONESIA |  |  |  | CL-GA00015
4945004 | Rekondisi pitot | 91 | FINANCIALLY CLOSED | R | Maintenance Request | 3 | WIthin a Week - Default | CL-GA00015 | HP F/S SUPPLY PUMP 1 (EAST) | Done | CL-HP4420 | 2020-11-03 | 2020-11-03 | 2020-11-03 |  | 24/04/20 |  | . | 100 | 4 |  | 11764420 | Raw Material Handling | 1175 | PT CABOT INDONESIA | 22415 | MULYADI HARIS ABDULLAH |  |  | 807400 | HENDRO CAHYONO |  |  | 04945004 | CL-GA00015 | CL | Cilegon | 20 | OPERATING MAINTENANCE | 7K | RAW MATERIAL HANDLING | 45 | OTHER |  | NO SHUT DOWN REQUIRED |  | NO PRIMARY CRAFT |  | NO CALL OUT REQUIRED | 515 | PUMP |  | Criticality Not Defined |  | . | WM | MAINTENANCE WORK ORDERS | 4 |  |  | 11761200 | MAINTENANCE - Cilegon |  | 1175 | PT CABOT INDONESIA |  |  |  | CL-GA00015